## schedule
XeHE
Task Name | Resource Names | Duration Estimate (weeks) | Duration Estimate (days) | Start | Finish | Predecessors / Dependencies
Phase I
Investigate basic operation implementation in competitor's GPU libs | Alexey/Alexander | 1 | 7
Familiarity with algorithms in SEAL: plaintext -> ciphertext, RNS (CRT/iCRT) | Alexey/Alexander | 1
Setup functional tests against the latest SEAL | Alexey | 1 | 7 | 2021-01-02 | 2021-01-08
Development and data movement framework on GPU | Alexey | 1
Verify basic ops working in DPC++ for integer arithmetics | Alexander | 1
Basic modulo arithmetic in DPC++ for (uint32/64) | Alexey/Alexander | 6 | 21 | 2021-01-08 | 2021-01-28
DPC++ permormance measurement/estimation of basic modulo arithmetic | Alexander | 1
Prepare phase summary and report out | Alexey/Alexander | 1
Phase I Checkpoint |  |  | 0 | 2021-04-01 | 2021-04-01
Phase II |  |  | 0
Transform from extended integer to/from RNS
Implement modulo arithmetics add, sub for vector module p_i |  | 2
MUL in RNS |  | 2
Inverse/DIV in RNS |  | 2
Polynomial MUL (brute force)
Polynomial ADD
Familiarity with NTT/iNTT |  | 2
NTT/iNTT tranform in DPC++
Polynomial MUL (NTT/iNTT)
HE basic arithmetics works on GPU |  | 2 | 0
0
0
0
Prepare phase summary and report out |  | 1 | 0
Phase II Checkpoint |  |  |  | 2021-09-01 | 2021-09-01
Phase III
Extendeded integer arithmetics (up to 4k bit)
Extendeded modulo integer arithmetics (up to 4k bit)
HE basic demo evaluation works end-to-end |  | 2 | 0
A few HE benchmark cases defined and performance measured |  | 3 | 0
EVA compute graph tool evaluated and tested for XeHE |  | 3 | 0
6
2
3
4
Prepare phase summary and report out |  | 1
Phase III Checkpoint |  |  |  | 2021-12-01 | 2021-12-01
Phase IV
Optimization pass for HE |  | 6
More HE benchmark cases defined |  | 2
Additional HE benchmark cases implemented |  | 3
Workload experimentation for better GPU mapping |  | 4
Formulas:
Duration Estimate (days) = DATEDIF([Start],[Finish],"d")+1
Duration Estimate (days) = DATEDIF([Start],[Finish],"d")

## Sheet1
template <typename T>
void multiply(
const T *operand1,
size_t operand1_uint64_count,
const T *operand2,
size_t operand2_uint64_count,
size_t result_uint64_count,
T *result)